## NEW-Requirment & CR
Sr. No | Modules | Task Name | UAT Date | Activity Status | Production Deployement | Remarks | Comment resolution time | Prod Deployment
1 | OBPAS | Installment feature for OBPAS | 2022-07-17 | Completed | Delayed | Signoff Pending from BDA for Production deployement | 3 | 2022-07-20
2 | OBPAS | Approval by Accredited Person | 2022-07-18 | 1st UAT completed 2nd UAT to be done on 20/07 for sign off | On Schedule |  | 3 | 2022-07-21
4 | OBPAS | Pre-Approved Plan for OBPAS | 2022-07-22 | Completed | On Schedule |  | 3 | 2022-07-27
5 | OBPAS | SPARIT Implementation completion | 2022-07-22 | Completed | On Schedule |  | 3 | 2022-07-27
11 | OBPAS | Revision Service | 2022-07-28 | New Requirment pendding |  |  | 3 | 2022-08-02
14 | OBPAS | OBPAS -Mixed Use | 2022-08-16 | In progress |  |  | 3 | 2022-08-19
15 | OBPAS | Sub-occupancy wise fee calculation in OBPAS | 2022-08-16 | UAT Deployed |  |  | 3 | 2022-08-19
18 | OBPAS | AAI NOC Integration for OBPAS | 2022-08-29 | Development Pending |  |  | 3 | 2022-09-01
31 | OBPAS | GIS Integration analysis & requirement finalization & Resolution time submission | 2022-07-22 | Requirement Discussion to be done tomorrow
Formulas:
Prod Deployment = WORKDAY([UAT Date],[Comment resolution time])

## Tasks
Category | Task | Assigned to
Pre Approved | Notified drawing number need to be added to permit certificate | Ankit | deployed
| BP6 permit letter generation with respect to BP1 | Ankit | deployed
| Pre approved employee creation in production for adding drawing | Freddy and Upasana
| 104 drawings upload in production | Freddy
AAI NOC | Testing with AAI team | Pennding from AAI Team
Post Testing Enhancement
Revision Service | For applications which received permit letter from SUJOG, The scrutiny report should include the comparison report between the earlier scrutiny details and the new scrutiny details | Reza
| Permit details section to be renamed to Permit Letter Number | Digdarshan | deployed
| In case the applicant has provided permit number that is generated outside sujog, The system to give message ' No records found for the given permit number in SUJOG database' | Digdarshan | deployed
| When the applicant fills the permit number, the format of the same should be already present in the system, so as to reduce chances of mistake from the architects side | Digdarshan | deployed
| Only keep Mobile number, Email and Applicant name, Address fields as mandatory in the owners information section. (this has to be done for all OBPAS services) | Digdarshan + PK | deployed
| For applications which received permit letter from SUJOG, if the applicant enters permit number which is expired now, the system should show a message informing the Architect to apply for a fresh application | Digdarshan | deployed
| Namita Maam to share the format of the Permit letter for this service. | BDA
Addition & Alteration | 2 service option when addition alteration is selected
1 service - checkbox with message 'existing Construction is done within the validity of permit order. If the architect does not check this then the scrutiny will not be allowed to take place and a message will be shown stating The existing area is unauthorized and needs to be regularized before applying for addition & alteration'
Report | 1 | Ankit
2
3
4
5
6
Workflow | Need to update BPA1,BPA2,BPA3 need to update | PK
Prod bug
Mixed Use | BDA Observations | Reza + Freddy

## Production Issue
Ticket No | Application No | Issue Category | Ticket Deatails | Reported Date | Status | Assign To | Solution Details | UAT Date | Production Date | Additonal Details
Ticket/2022/3658 | BPR-2021-09-06-000432 | Architect Registration | Architect Registration approval issue - Error 'User Permanent address cannot be nul ' while approving application | ongoing issue few instance recorded | Resolved - UAT Deployed Pending | ANKIT | uat deployment pending of code
Ticket/2022/3905 | BPR-2022-08-04-003070 | Architect Registration | Official unable to reject architect registration applicaion - create api failed with error message - user permanent address cannot be null | 2022-09-06 | Resolved - UAT Deployed Pending | ANKIT | changed the backend code uat deployment pending
Ticket/2022/3674 |  | Scrutiny | Dcr no. shown in "my application" page is different from scrutiny report. | 2022-08-13 | Resolved - Prod Deployed Pending | Digdarshan,Reza |  |  |  | Back-end all fine, Need to check from UI
Ticket/2022/3607 | BP-BMC-2022-05-29-003846 | Application | application is not visible to official for signing drawing after permit letter has been signed | 2022-08-26 | Closed
Ticket/2022/3646 | BP-BMC-2022-03-14-001661 | Application | application is not visible to official for signing drawing after permit letter has been signed | 2022-08-24 | Closed
Ticket/2022/3616 | BP-BMC-2022-03-14-001662 | Application | application is not visible to official for signing drawing after permit letter has been signed | 2022-08-24 | Closed
Ticket/2022/3622 | BP-BMC-2022-03-30-002031 | Application | application is not visible to official for signing drawing after permit letter has been signed | 2022-08-24 | Closed
Ticket/2022/3633 |  | Scrutiny | Scrutiny report is reading not reading individual floor carpet area, but is reading total carpet area | 2022-08-24 | Open | Reza
Ticket/2022/3664 | BP-BMC-2022-01-29-000585 | Permit Letter | Road width, occupancy and rear set back are wrong in permit order | 2022-08-21 | Closed | PK
Ticket/2022/3659 |  | Scrutiny | Drawing for coaching center with colour code 170 is not being read by scrutiny | 2022-08-26 | Closed
Ticket/2022/3854 | BP-BMC-2022-08-08-007278 | Application | For addidtion & alteration case, fee is being charged on both proposed and existing areas | 2022-08-26 | Closed
Ticket/2022/3895 | BP-BMC-2022-07-14-006105 | Permit Letter | Permit letter not reflecting only paid installment as full fees | 2022-09-02 | Resolved - UAT Deployed Pending | PK
Ticket/2022/3904 | BP-BMC-2022-03-04-001358 | Application | Official unable to see application in all/ assign to me section. only visible in BPA search | 2022-09-05 | Closed | PK
Ticket/2022/3999 | BP-BMC-2022-03-04-001372 | Application | Official unable to view application for signing building plan | 2022-09-07 | Closed
Ticket/2022/3980 | BP-BMC-2022-03-09-001548 | Application | Official unable to view application for signing building plan | 2022-09-07 | Closed
Ticket/2022/3951 | BP-BMC-2022-04-30-003049 | Application | link to upload signed building plan not showing | 2022-09-06 | Closed
Ticket/2022/3986 | BPR-2022-04-30-002414 | Architect Registration | while registering for technical person applicant is unable to move on next page | 2022-09-08 | Resolved - UAT Deployed Pending | Digdarshan,ANKIT
Ticket/2022/3981 | BP-BMC-2022-06-13-004671 | Application | Official unable to view application for signing building plan | 2022-09-08 | Closed
Ticket/2022/4083 |  | Application | Increase limit of 5mb for uploading signed document -> 30MB | 2022-09-09 | In Progress - backend Pendding | Digdarshan,ANKIT | I have fixed it from UI side . Needs to be fixed from backend side.
Ticket/2022/4070 | BP-BDA-2022-03-08-001474 | DSC | error while signing application - error in update call post pdf sign | 2022-09-09 | Open
Ticket/2022/4081 | BP-BDA-2022-05-30-003857 | Application | the application approved by planning officer is visible to planning assitant for signing drawing | 2022-09-09 | Resolved - Prod testing Pending |  |  |  |  | need to confirm sign button
Ticket/2022/3655 | BP-BDA-2022-08-26-007851 | Scrutiny | Land development fee is charged in application even though the required info is provided in plan info | 2022-08-26 | In Progress | PK
Ticket/2022/3867 | BP-BDA-2022-06-12-004652 | NOC | NMA noc triggered automatically - as per plan info provided it should not be triggered | 2022-09-04 | Closed | PK |  |  |  | already no noc present
|  | Application | comment send by official to another official is visble to citizen |  | Resolved - Prod Deployed Pending | DD
| BP-BMC-2022-03-15-001707 | Other | currently file is pending for rework - send it one step back | 2022-09-12 | Closed
Ticket/2022/4175 | BP-BDA-2022-04-20-002668 | Multiple document | doc verifier is unable to forward file - multiple doc error | 2022-09-08 | Resolved - Prod testing Pending | PK
Ticket/2022/4151 | BP-BDA-2022-08-08-007297 | Multiple document | doc verifier is unable to forward file - multiple doc error | 2022-09-08 | Resolved - Prod testing Pending | PK
Ticket/2022/4038 | BP-RRK-2022-08-03-007048 | Status Mismatch | status mismatched- after fixing again got stuck | 2022-09-13 | Re-Open
Ticket/2022/4044 | BPR-2022-08-31-003228 | Architect Registration | official unable to approve error - Workflow returned empty object | 2022-09-13 | Resolved - Prod testing Pending | ANKIT |  |  |  | Application is not submited by Arch
Ticket/2022/1363 | BPR-2022-01-20-001363 | Architect Registration | application approved still architect role is not assigned even after fixing | 2022-09-16 | Closed | PK
Ticket/2022/4158 |  | Scrutiny | club house in residential project is being read as mixed use in scrutiny report | 2022-09-12 | Open
Ticket/2022/4116 |  | Scrutiny | Scrutiny is asking for Special Lift and maximum travel distance though not required | 2022-09-08 | Closed
Ticket/2022/4081 | BP-BDA-2022-05-30-003857 | Application | the application approved by planning officer is visible to planning assitant for signing drawing | 2022-09-09 | Resolved - Prod testing Pending | Ankit & Digdarshan
|  | Application | doc verifier is unable to forward file - update api failed with error: 413 rquest entity too large |  | Open
|  |  | land info service failed while filling multiple owners |  | Open | Ankit
Ticket/2022/3855 | BP-BDA-2022-04-30-003067 | NOC | NMA noc triggered automatically - as per plan info provided it should not be triggered | 2022-09-19 | Re-Open | PK

## Open Issue
ISSUE DETAIL: | APPLICATION NO. | RECEIVED DATE: | STATUS:
Mouza-patapur, It is coming under Cuttack development Authority. But in Sujog it shows in Cuttack municipal corporation | BP-CTC-2022-04-22-002747 | 15/05/2022 | Closed
Make payment option is not visible - Need remove last process Instance | BP-BDA-2022-03-26-001959 | 20/07/2022 | Closed
Scrutiny button not showing after successful architect registration | BPR-2022-01-10-001068 | 24/04/2022 | Resolved | user has correct role
Scrutiny button not showing after successful architect registration | BPR-2022-01-20-001363 | 28/05/2022 | Resolved | user has correct role
Architect Registration approval issue - Error 'User Permanent address cannot be nul ' while approving application | BPR-2021-09-06-000432 | ongoing issue few instance recorded | OPEN | In Progress
Submitted Architect Registration application shows 0 documents | BPR-2022-06-29-002869 | 17/07/2022 | Resolved | Application already rejected plz create new application
While signing permission letter the preview is different from the signed one |  | 27/07/2022 | Resolved | In Progress | Fix from UI wait for next deployment
Processing time issue for one file in auto-scrutiny |  | 14/07/2022 | Resolved | critical | Meeting with Egov to discuss
Public washroom error in scrutiny report |  | 18/07/2022 | Resolved | critical | In progress - Suggestion by jatinder
Applicant unable to forward application to authority- error: rate limit exceeded Now multiple document issue | BP-BMC-2022-05-04-003189 | 18/08/2022 | Resolved | critical | Input from BA Team | not resolved
Dcr no. shown in "my application" page is different from scrutiny report. |  | 13/08/2022 | not Closed
error while approving same document cannot be uploaded multiple times, also both Fire and NMA NOC to be removed | BP-BDA-2022-07-07-005886 | 23/08/2022 | Resolved
wrong date in permit order | BP-CTC-2022-07-23-006490 | 23/08/2022 | Resolved | Need to regenrate PL
wrong date in permit order | BP-CTC-2022-08-03-007081 | 23/08/2022 | Resolved | Need to regenrate PL
wrong date in permit order | BP-CTC-2022-06-23-005066 | 23/08/2022 | Resolved | Need to regenrate PL
wrong date in permit order | BP-CTC-2022-05-31-003916 | 24/08/2022 | Resolved | Need to regenrate PL
wrong date in permit order | BP-BMC-2022-04-13-002509 | 25/08/2022 | Resolved | Need to regenrate PL
Status is pending for field inspection but is not visible to field inspector | BP-BMC-2022-04-30-003061 fieldinspector user id - SUJOG_EMP_2348, 7873598994 | 23/08/2022 | closed | Application not vissible in inbox, But can able to acess it from bpa search. Employee need to do field infection and then will see
Officials are unable to see attached document in the application at times - filestoreid fail |  | 20/08/2022 | Resolved | critical
Officials are unable to sign, updatdscdetail api failed - error : DSC detail error - DSC details can only be signed by the person who approved it | BP-BDA-2022-07-12-006013 | 25/08/2022 | Resolved |  | Changed approval
wrong date in permit order | BP-BMC-2022-06-13-004671 | 26/08/2022 | Resolved | Need to regenrate PL
wrong date in permit order | BP-BMC-2022-07-22-006454 | 26/08/2022 | Resolved | Need to regenrate PL
application is not visible to official for signing drawing after permit letter has been signed - while opening application file store id fails with rate limit exception | BP-BMC-2022-05-29-003846 | 26/08/2022 | Resolved | not resolved
application is not visible to official for signing drawing after permit letter has been signed - while opening application file store id fails with rate limit exception | BP-BMC-2022-03-14-001661 | 24/08/2022 | Resolved | not resolved
application is not visible to official for signing drawing after permit letter has been signed - while opening application file store id fails with rate limit exception | BP-BMC-2022-03-14-001662 | 24/08/2022 | Resolved | not resolved
application is not visible to official for signing drawing after permit letter has been signed - while opening application file store id fails with rate limit exception | BP-BMC-2022-03-30-002031 | 24/08/2022 | Resolved | not resolved
Remove Noc - triggered by applicant bymistake | BP-BMC-2022-08-17-007534 | 26/08/2022 | Resolved | In Progress
NMA noc triggered automatically - as per plan info provided it should not be triggered | BP-BED-2022-07-05-005801 | 26/08/2022 | Resolved | Need more info from applicant | Deleted noc
Scrutiny report is not reading a field from plan info, though provided in right format |  | 23/08/2022 | Resolved | In Progress | Reza is checking the issue
Scrutiny report is not reading setbacks, though provided in right format |  | 25/08/2022 | Resolved | In Progress | Reza is checking the issue |  | inprogress
Error in scrutiny report - Please contact the adminstrator for the further information. The plan is failing while extracting data from plan in the feature org.egov.edcr.feature.FarExtract@43c4a2a |  | 22/08/2022 | Resolved | In Progress | Reza is checking the issue
Scrutiny report is reading not reading individual floor carpet area, but is reading total carpet area |  | 24/08/2022 | OPEN | In Progress | Reza is checking the issue
Make payment option is not visible - status mis match also delete NMA noc as it has been triggered by mistake | BP-BDA-2022-08-06-007232 | 27/08/2022 | Resolved
Official unable to view permit letter after signing - permitorderdcr api failed : zul run time exception error | BP-BDA-2022-08-04-007138 | 26/08/2022 | Resolved
Land development fee is charged in application even though the required info is provided in plan info | BP-BDA-2022-08-26-007851 | 26/08/2022 | Ticket closed but need to be fixed
Road width, occupancy and rear set back are wrong in permit order | BP-BMC-2022-01-29-000585 | 21/08/2022 | OPEN
Drawing for cochinng center with colour code 170 is not being read by scrutiny |  | 26/08/2022 | OPEN | In Progress | Reza is checking the issue
For addition
PDF file issue rita | BP-BDA-2022-08-04-007138 | 2022-05-09 | Resloved | Send back for re sign
Status mismatch non approved action | BP-BAM-2022-08-07-007249 BP-BDA-2022-07-05-005767 BP-BDA-2022-08-08-007269 BP-BMC-2022-04-05-002204 BP-BMC-2022-07-07-005901 BP-BMC-2022-08-17-007537 BP-BMC-2022-08-21-007654 BP-BMC-2022-08-28-007889- not fixed BP-JTN-2022-04-28-002999 BP-JTN-2022-08-03-007071 BP-SMB-2022-07-12-006045 BP-TAM-2022-08-06-007240 | 2022-05-09 | Resloved
Payment status issue | BP-BDA-2022-03-08-001474 BP-BMC-2022-08-29-007918 BP-BMC-2022-08-29-007927 BP-BMC-2022-08-29-007930 BP-KHU-2022-08-22-007682 | 2022-05-09 | Resloved | Tapojit
Status mismatch with approved action | BP-BDA-2022-04-21-002725 BP-BDA-2022-08-06-007232 | 2022-05-09 | Resloved | Send back to approve again
For addidtion & alteration case, fee is being charged on both proposed and existing areas
Permit letter not reflecting only paid installment as full fees | BP-BMC-2022-07-14-006105
Unable to make payment - no demand found error | BP-SMB-2022-04-25-002844 |  | Resloved
NMA noc triggered automatically - as per plan info provided it should not be triggered | BP-BDA-2022-04-30-003067 |  | Resloved
NMA noc triggered automatically - as per plan info provided it should not be triggered | BP-BMC-2022-06-12-004652 |  | Resloved | BP-BDA-2022-06-12-004652 |  | EIDP FEE PAID IN KHURDA DRDA NEED TO CONFIRM WITH OFFICIALS
NMA noc triggered automatically - as per plan info provided it should not be triggered | BP-BMC-2022-03-01-001255 |  | Resloved
Remove NMA Noc | BP-JTN-2022-08-03-007071 |  | Resloved
Remove Fire NOC | BP-RRK-2022-04-30-003077 |  | Resloved
wrong date in permit order | BP-BMC-2022-04-29-003037 |  | Resloved
wrong date in permit order | BP-BDA-2022-07-03-005673 |  | Resloved
Official has been transfered, change approver to deepal sir : uuid: "b16fa518-63f9-4529-96a5-1bfe79dbc44e" | BP-BED-2022-04-18-002597 |  | Resloved
Official unable to see file in all/ assign to me section only visible in BPA Search | BP-BMC-2022-03-04-001358
comment send by official to another official is visble to citizen
Official unable to reject architect registration applicaion - create api failed with error message - user permanent address cannot be null | BPR-2022-08-04-003070
Official unable to view application for signing building plan | BP-BMC-2022-03-04-001372
Official unable to view application for signing building plan | BP-BMC-2022-03-09-001548
Official unable to view application for signing building plan | BP-BMC-2022-06-13-004671
link to upload signed building plan not showing | BP-BMC-2022-04-30-003049
status mismatched | BP-RRK-2022-08-03-007048 | Resloved
status mismatched | BP-BMC-2022-09-04-008099 | Resloved
status mismatched | BP-BMC-2022-09-02-008032 | Resloved
status mismatched | BP-BAM-2022-08-29-007910 | Resloved
status mismatched | BP-BDA-2022-08-08-007269 | Resloved
While registeriing for technical person applicant is unable to move on next page - (eirlier file store id failed with ratelimit exceeded error after fix by prateek no api is failed but still applicant is unable to go to next page) | 9778811114
increase limit of 5 mb for uploading digitally signed doc
currently file is pending for rework - send it one step back | BP-BMC-2022-03-15-001707
error while signing the application - error in update call post pdf sign | BP-BDA-2022-03-08-001474
The application has been approved by the planning officer (namita mohanty) but is visible to the planning assistant (rita patnaik)for signing drawing | BP-BDA-2022-05-30-003857

## Ref-data
Issue Category | Status
Permit Letter | Open
Payment Issue | In Progress
Status Mismatch | In Progress - UI Pendding
NOC | In Progress - backend Pendding
Architect Registration | In Progress - DB query excution Pendding
Scrutiny | Need Additional Deatils
Application | Resolved - UAT Deployed Pending
DSC | Resolved - Prod Deployed Pending
Other | Resolved - Prod testing Pending
Multiple document | Closed
Re-Open